## Dashboard
10
TEKNOSYS · TELECOM DW ¦ Release Tracker Dashboard | [7 empty] | 2026
Live from the Release Calendar sheet · nothing to fill in here · as of 14 Oct 2026 | [7 empty] | 2026-10-01
2026-10-31
OVERALL
TOTAL RELEASES |  | OPEN |  | COMPLETED |  | DUE SOON (≤ 3 DAYS)
37 |  | 6 |  | 31 |  | 0
Completion rate | ████████████████████████████████████████░░░░░░░░ | [5 empty] | 83.78%
BY PLATFORM |  |  |  | BY DEPLOYMENT TYPE
DPI | 0 |  | 0% | Scheduled | 32 | ████████████ | 86.49%
APIs | 2 | █ | 5.405% | Emergency | 1 |  | 2.703%
GSM | 25 | █████████ | 67.57% | Hotfix | 4 | ██ | 10.81%
DFS | 9 | ███ | 24.32%
BI | 0 |  | 0%
BY STATUS |  |  |  | BY STAGE
On Track | 0 |  | 0% | Development | 0 |  | 0%
At Risk | 0 |  | 0% | SIT | 0 |  | 0%
Delayed | 0 |  | 0% | UAT | 1 |  | 2.703%
Completed | 31 | ████████████ | 83.78% | CAB / RFC | 0 |  | 0%
On Hold | 2 | █ | 5.405% | Code Freeze | 0 |  | 0%
|  |  |  | Pre-Prod | 5 | ██ | 13.51%
HOLIDAYS |  |  |  | Production | 28 | ███████████ | 75.68%
Holiday conflicts | 0 |  |  | Completed | 3 | █ | 8.108%
Holidays defined | 21 |  |  | On Hold | 0 |  | 0%
OCTOBER 2026 — MONTHLY VIEW
Releases whose Target Deploy falls in the selected month · change Month / Year below (defaults to the current month)
Month: | 10 | Year: | 2026 | October 2026
TOTAL RELEASES |  | OPEN |  | COMPLETED |  | DUE SOON (≤ 3 DAYS)
4 |  | 3 |  | 1 |  | 0
Completion rate | ████████████░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░ | [5 empty] | 25%
BY PLATFORM |  |  |  | BY DEPLOYMENT TYPE
DPI | 0 |  | 0% | Scheduled | 3 | ███████████ | 75%
APIs | 0 |  | 0% | Emergency | 0 |  | 0%
GSM | 2 | ███████ | 50% | Hotfix | 1 | ████ | 25%
DFS | 2 | ███████ | 50%
BI | 0 |  | 0%
BY STATUS |  |  |  | BY STAGE
On Track | 0 |  | 0% | Development | 0 |  | 0%
At Risk | 0 |  | 0% | SIT | 0 |  | 0%
Delayed | 0 |  | 0% | UAT | 0 |  | 0%
Completed | 1 | ████ | 25% | CAB / RFC | 0 |  | 0%
On Hold | 0 |  | 0% | Code Freeze | 0 |  | 0%
|  |  |  | Pre-Prod | 1 | ████ | 25%
HOLIDAYS |  |  |  | Production | 3 | ███████████ | 75%
Holiday conflicts | 0 |  |  | Completed | 0 |  | 0%
|  |  |  | On Hold | 0 |  | 0%
HOW TO USE
1. Enter / update releases only on the 'Release Calendar' sheet — yellow cells only.
2. Use the dropdowns for Platform, Deployment Type, Stage, Owner and Status.
3. The Holiday Conflict column flags releases planned on a holiday — fix red flags before status meetings.
4. This dashboard and the calendar / Gantt sheets update automatically — do not edit them.
5. Ask the Release Manager to update any dropdown list if new values are needed.

## Holidays
TEKNOSYS · TELECOM DW ¦ Holiday Blackout Calendar
Add holidays here. Target Deploy dates falling on any listed holiday will be blocked automatically.
For a single-day holiday, put the same date in both Start Date and End Date. Multi-day holidays span the whole range inclusive.
# | Holiday Name | Start Date | End Date | Notes | Row Check
1 | Kashmir Day | 2026-02-05 | 2026-02-05 | Fixed public holiday | OK
2 | Eid-ul-Fitr | 2026-03-20 | 2026-03-21 | Tentative (moon sighting) | OK
3 | Pakistan Day | 2026-03-23 | 2026-03-23 | Fixed public holiday | OK
4 | Labour Day | 2026-05-01 | 2026-05-01 | Fixed public holiday | OK
5 | Eid-ul-Adha | 2026-05-27 | 2026-05-29 | Tentative (moon sighting) | OK
6 | Ashura (9th-10th Muharram) | 2026-06-24 | 2026-06-25 | Tentative (Islamic calendar) | OK
7 | Independence Day | 2026-08-14 | 2026-08-14 | Fixed public holiday | OK
8 | Eid Milad-un-Nabi | 2026-08-25 | 2026-08-25 | Tentative (moon sighting) | OK
9 | Iqbal Day | 2026-11-09 | 2026-11-09 | Fixed public holiday | OK
10 | Quaid-e-Azam Day / Christmas | 2026-12-25 | 2026-12-25 | Fixed public holiday | OK
11 | Kashmir Day | 2027-02-05 | 2027-02-05 | Fixed public holiday | OK
12 | Eid-ul-Fitr | 2027-03-10 | 2027-03-12 | Tentative (moon sighting) | OK
13 | Pakistan Day | 2027-03-23 | 2027-03-23 | Fixed public holiday | OK
14 | Labour Day | 2027-05-01 | 2027-05-01 | Fixed public holiday | OK
15 | Eid-ul-Adha | 2027-05-17 | 2027-05-18 | Tentative (moon sighting) | OK
16 | Youm-e-Takbeer | 2027-05-28 | 2027-05-28 | Fixed public holiday | OK
17 | Ashura (9th-10th Muharram) | 2027-06-14 | 2027-06-15 | Tentative (Islamic calendar) | OK
18 | Independence Day | 2027-08-14 | 2027-08-14 | Fixed public holiday | OK
19 | Eid Milad-un-Nabi | 2027-08-15 | 2027-08-15 | Tentative (moon sighting) | OK
20 | Iqbal Day | 2027-11-09 | 2027-11-09 | Fixed public holiday | OK
21 | Quaid-e-Azam Day / Christmas | 2027-12-25 | 2027-12-25 | Fixed public holiday | OK
22
23
24
25
26
27
28
29
30

## Release Calendar
TEKNOSYS · TELECOM DW ¦ Release Tracker
Each release is tracked independently · update Current Stage and Status as it moves forward
✎ Fill in the yellow columns (use the dropdowns for Platform, Type, Stage, Owner and Status; dates as yyyy-mm-dd). ■ The grey-green Holiday Conflict column is automatic — do not edit.
# | Release Name | RITM | CR | Developer Name | Version / Tag | Platform | Deployment Type | Start Date | Target Deploy | Current Stage | Stage Owner | Status | DB Objects Changed | Notes / Blockers | Email | Holiday Conflict
1 | BVS Sales Old Age flag Core |  |  | Rabia Qayyum | v1 | GSM | Scheduled | 2026-08-04 | 2026-08-12 | Production | Ops Team | Completed |  | Nothing
2 | OMNI API table export |  |  | Mahum Tariq | V1 | APIs | Scheduled | 2026-08-10 | 2026-08-12 | Production | Dev Team | Completed |  | NA
3 | Multiplay 90 Days (Pre and Post) |  |  | Ukasha Shafique | V1 | GSM | Scheduled | 2026-08-03 | 2026-08-18 | Production | Dev Team | Completed |  | None
4 | Addition in Universal Charging Base |  |  | Hafsa Malik | V1 | GSM | Scheduled | 2026-08-17 | 2026-08-19 | Production | Dev Lead | Completed |  | None
5 | postpaid lifecycle hotfix |  |  | Moeiz Bhatti | V1 | GSM | Hotfix | 2026-08-17 | 2026-08-17 | Production | Dev Team | Completed |  | NONE
6 | BVS Sales Old Age flag Semantic |  |  | Rabia Qayyum | V2 | GSM | Scheduled | 2026-08-12 | 2026-08-19 | Production | Dev Team | Completed |  | None
7 | UCIP_LKP update |  |  | Daniyal Ahmed | V1 | GSM | Scheduled | 2026-08-18 | 2026-08-19 | Production | Ops Team | Completed |  | None
8 | Daily Kpi Report - Addition of KPIs |  |  | Afia Abdul Rehman | V3 | DFS | Scheduled | 2026-09-02 | 2026-09-02 | Production | Ops Team | Completed |  | None
9 | Reward Hub Ceo Category |  |  | Abdul Wahab Malik | V1 | DFS | Emergency | 2026-09-01 | 2026-09-04 | Production | Release Manager | Completed |  | None
10 | Daily KPI Report- Addition of App Kpis |  |  | Afia Abdul Rehman | V10 | DFS | Scheduled | 2026-09-09 | 2026-09-09 | Completed | Release Manager | Completed |  | None
11 | Postpaid lifecycle DDLS fix |  |  | Moeiz Ali Bhatti | v1 | GSM | Scheduled | 2026-09-09 | 2026-09-09 | Production | Release Manager | Completed |  | None
12 | Jazz Advance TPT Update |  |  | Hafsa Malik | V1 | APIs | Scheduled | 2026-08-31 | 2026-08-31 | Completed | Ops Team | Completed |  | None
13 | Reward Hub - CEO addition |  |  | Abdul Wahab Malik | V1 | DFS | Scheduled | 2026-09-07 | 2026-09-10 | Completed | Dev Team | Completed |  | none
14 | Simosa Parent Child Sourcing |  |  | Daniyal Ahmed | V1 | GSM | Scheduled | 2026-09-08 | 2026-09-09 | Production | Dev Team | Completed |  | None
15 | live app hierarchy fix |  |  | Asfandyar Barki | v1 | GSM | Hotfix | 2026-08-09 | 2026-08-09 | Production | Dev Team | Completed
16 | Dekho - Digital Lifecycle Snapshot Discontinuation |  |  | Ahmad Faizan | v1 | GSM | Scheduled | 2026-09-08 | 2026-09-09 | Production | Dev Team | Completed |  | None
17 | DFS Lifecycle new columns addition |  |  | Muhammad Fawad Akhtar | v4 | DFS | Scheduled | 2026-09-16 | 2026-09-16 | Production | Dev Team | Completed
18 | lifecycle view fix for sbskey |  |  | Moeiz Bhatti | v1 | GSM | Scheduled | 2026-09-16 | 2026-09-16 | Production | Dev Team | Completed |  |  | sbscrpn_key tagging fix in 3 views of new lifecycle.
19 | SDS 5G Attributes Addition |  |  | Bilal Siddiqui | v1 | GSM | Scheduled | 2026-09-16 | 2026-09-16 | Production | Ops Team | Completed
20 | Rox Achievement Fix |  |  | Asfandyar Barki | v1 | GSM | Hotfix | 2026-09-21 | 2026-09-21 | Production | Dev Team | Completed |  |  | Re: Difference in Postpaid and ROX achievements in Datewise and in indivivdual reports ¦ RM-1990
21 | CPS License Log & Daily OFT Report |  |  | Waqar Saeed | v1 | DFS | Scheduled | 2026-09-10 | 2026-09-22 | UAT | Dev Team | Completed
22 | NBO Lookup - New Sourcing |  |  | Asfandyar Barki | v1 | GSM | Scheduled | 2026-09-23 | 2026-09-23 | Production | Dev Team | Completed
23 | Sales Fact 5G Date Addition |  |  | Bilal Siddiqui | v1 | GSM | Scheduled | 2026-09-25 | 2026-09-30 | Production | Dev Team | Completed
24 | postpaid live |  |  | moeiz bhatti | v1 | GSM | Scheduled | 2026-09-30 | 2026-09-30 | Production | Dev Team | Completed
25 | addition of KPIS in script dashboard day wise kpi |  |  | Fawad Akhtar | v2 | DFS | Scheduled | 2026-09-30 | 2026-09-30 | Production | Ops Team | Completed
26 | Postpaid Conversion API |  |  | Hafsa Malik | v1 | GSM | Scheduled | 2026-09-28 | 2026-09-30 | Pre-Prod | Dev Team | Completed
27 | Jazz Advance TPT Update |  |  | Hafsa Malik | V1 | GSM | Scheduled | 2026-09-28 | 2026-09-30 | Pre-Prod | Dev Team | Completed
28 | Jazz CX IVR API |  |  | Husinah Amir | V1 | GSM | Scheduled | 2026-09-28 | 2026-09-30 | Production | Dev Team | On Hold
29 | FikrFree New Sourcing |  |  | Ahmad Faizan | V1 | JLV | Scheduled | 2026-09-29 | 2026-09-30 | Production | Dev Team | On Hold
30 | MSPH COLUMN ADDITION |  |  | Tauseef haq | V1 | GSM | Scheduled | 2026-09-30 | 2026-09-30 | Production | Dev Team | Completed
31 | UCIP_LKP update (Gamenow Ucips) |  |  | Daniyal Ahmed | V1 | GSM | Scheduled | 2026-09-30 | 2026-09-30 | Pre-Prod | Dev Team | Completed
32 | 699 ODS – Subscriber Upgrade/Whitelisting Plan |  |  | Asfandyar Barki | v1 | GSM | Scheduled | 2026-09-30 | 2026-09-30 | Production | Dev Team | Completed
33 | Tamasha IP list update |  |  | Ahmad Faizan | V1 | GSM | Scheduled | 2026-10-07 | 2026-10-07 | Pre-Prod | Dev Team
34 | Reward Hub Ceo Category |  |  | Afia Abdul Rehman | V1 | DFS | Scheduled | 2026-10-07 | 2026-10-07 | Production |  | Completed
35 | Digital Funnel Daily and linked MP Marts - Tamasha Definition Update |  |  | Daniyal Ahmed |  | GSM | Scheduled | 2026-10-07 |  | Pre-Prod | Dev Team
36 | DFS Lifecycle new columns addition |  |  | Fawad Akhtar | v4 | DFS | Scheduled | 2026-10-12 | 2026-10-12 | Production
37 | b2c sales hotfix |  |  | Moeiz Bhatti | v1 | GSM | Hotfix | 2026-10-13 | 2026-10-13 | Production | Dev Team
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500

## Calendar View
TEKNOSYS · TELECOM DW ¦ Release Timeline 2026
Gantt bars run from Start Date to Target Deploy on the Release Calendar sheet · coloured by Status · highlighted column = current month
| Status key ▸ |  |  | On Track |  | At Risk |  | Delayed |  | Completed |  | On Hold |  | ★ this month
# | Release Name | Current Stage | Status | Jan 2026 | Feb 2026 | Mar 2026 | Apr 2026 | May 2026 | Jun 2026 | Jul 2026 | Aug 2026 | Sep 2026 | Oct 2026 | Nov 2026 | Dec 2026
1 | BVS Sales Old Age flag Core | Production | Completed | [7 empty] | █ |  |  |  |  | 2026-08-04 | 2026-08-12
2 | OMNI API table export | Production | Completed | [7 empty] | █ |  |  |  |  | 2026-08-10 | 2026-08-12
3 | Multiplay 90 Days (Pre and Post) | Production | Completed | [7 empty] | █ |  |  |  |  | 2026-08-03 | 2026-08-18
4 | Addition in Universal Charging Base | Production | Completed | [7 empty] | █ |  |  |  |  | 2026-08-17 | 2026-08-19
5 | postpaid lifecycle hotfix | Production | Completed | [7 empty] | █ |  |  |  |  | 2026-08-17 | 2026-08-17
6 | BVS Sales Old Age flag Semantic | Production | Completed | [7 empty] | █ |  |  |  |  | 2026-08-12 | 2026-08-19
7 | UCIP_LKP update | Production | Completed | [7 empty] | █ |  |  |  |  | 2026-08-18 | 2026-08-19
8 | Daily Kpi Report - Addition of KPIs | Production | Completed | [8 empty] | █ |  |  |  | 2026-09-02 | 2026-09-02
9 | Reward Hub Ceo Category | Production | Completed | [8 empty] | █ |  |  |  | 2026-09-01 | 2026-09-04
10 | Daily KPI Report- Addition of App Kpis | Completed | Completed | [8 empty] | █ |  |  |  | 2026-09-09 | 2026-09-09
11 | Postpaid lifecycle DDLS fix | Production | Completed | [8 empty] | █ |  |  |  | 2026-09-09 | 2026-09-09
12 | Jazz Advance TPT Update | Completed | Completed | [7 empty] | █ |  |  |  |  | 2026-08-31 | 2026-08-31
13 | Reward Hub - CEO addition | Completed | Completed | [8 empty] | █ |  |  |  | 2026-09-07 | 2026-09-10
14 | Simosa Parent Child Sourcing | Production | Completed | [8 empty] | █ |  |  |  | 2026-09-08 | 2026-09-09
15 | live app hierarchy fix | Production | Completed | [7 empty] | █ |  |  |  |  | 2026-08-09 | 2026-08-09
16 | Dekho - Digital Lifecycle Snapshot Discontinuation | Production | Completed | [8 empty] | █ |  |  |  | 2026-09-08 | 2026-09-09
17 | DFS Lifecycle new columns addition | Production | Completed | [8 empty] | █ |  |  |  | 2026-09-16 | 2026-09-16
18 | lifecycle view fix for sbskey | Production | Completed | [8 empty] | █ |  |  |  | 2026-09-16 | 2026-09-16
19 | SDS 5G Attributes Addition | Production | Completed | [8 empty] | █ |  |  |  | 2026-09-16 | 2026-09-16
20 | Rox Achievement Fix | Production | Completed | [8 empty] | █ |  |  |  | 2026-09-21 | 2026-09-21
21 | CPS License Log & Daily OFT Report | UAT | Completed | [8 empty] | █ |  |  |  | 2026-09-10 | 2026-09-22
22 | NBO Lookup - New Sourcing | Production | Completed | [8 empty] | █ |  |  |  | 2026-09-23 | 2026-09-23
23 | Sales Fact 5G Date Addition | Production | Completed | [8 empty] | █ |  |  |  | 2026-09-25 | 2026-09-30
24 | postpaid live | Production | Completed | [8 empty] | █ |  |  |  | 2026-09-30 | 2026-09-30
25 | addition of KPIS in script dashboard day wise kpi | Production | Completed | [8 empty] | █ |  |  |  | 2026-09-30 | 2026-09-30
26 | Postpaid Conversion API | Pre-Prod | Completed | [8 empty] | █ |  |  |  | 2026-09-28 | 2026-09-30
27 | Jazz Advance TPT Update | Pre-Prod | Completed | [8 empty] | █ |  |  |  | 2026-09-28 | 2026-09-30
28 | Jazz CX IVR API | Production | On Hold | [8 empty] | █ |  |  |  | 2026-09-28 | 2026-09-30
29 | FikrFree New Sourcing | Production | On Hold | [8 empty] | █ |  |  |  | 2026-09-29 | 2026-09-30
30 | MSPH COLUMN ADDITION | Production | Completed | [8 empty] | █ |  |  |  | 2026-09-30 | 2026-09-30
31 | UCIP_LKP update (Gamenow Ucips) | Pre-Prod | Completed | [8 empty] | █ |  |  |  | 2026-09-30 | 2026-09-30
32 | 699 ODS – Subscriber Upgrade/Whitelisting Plan | Production | Completed | [8 empty] | █ |  |  |  | 2026-09-30 | 2026-09-30
33 | Tamasha IP list update | Pre-Prod | [10 empty] | █ |  |  | 2026-10-07 | 2026-10-07
34 | Reward Hub Ceo Category | Production | Completed | [9 empty] | █ |  |  | 2026-10-07 | 2026-10-07
35 | Digital Funnel Daily and linked MP Marts - Tamasha Definition Update | Pre-Prod | [13 empty] | 2026-10-07
36 | DFS Lifecycle new columns addition | Production | [10 empty] | █ |  |  | 2026-10-12 | 2026-10-12
37 | b2c sales hotfix | Production | [10 empty] | █ |  |  | 2026-10-13 | 2026-10-13
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
★ Highlighted column = current month (Oct 2026) ¦ Gantt bars auto-update from Release Calendar dates
LEGEND
█ On Track — on schedule |  |  |  |  | █ At Risk — delays possible |  |  |  |  | █ Delayed — behind schedule
█ Completed — deployed |  |  |  |  | █ On Hold — paused |  |  |  |  | ★ Current month (Oct 2026)

## Monthly Calendar
TEKNOSYS · TELECOM DW ¦ Monthly Release Calendar
Jira-style month view · chips are pulled live from the Release Calendar sheet (Start / Target Deploy)
Month: | 10 | Year: | 2026 | October 2026 |  |  | 2026-10-01 | 5 | 31
SUN | MON | TUE | WED | THU | FRI | SAT
|  |  |  | 2026-10-01 | 2026-10-02 | 2026-10-03
2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10
● Tamasha IP list update · Start ● Tamasha IP list update · Target
2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17
| ● DFS Lifecycle new columns addition · Start ● DFS Lifecycle new columns addition · Target | ● b2c sales hotfix · Start ● b2c sales hotfix · Target
2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24
2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31
STATUS LEGEND
On Track | At Risk | Delayed | Completed | On Hold
★ Highlighted date = today ¦ Change Month/Year above to view any period ¦ Chips & colors pull live from the Release Calendar sheet — no manual updates needed.

## Year Calendar
TEKNOSYS · TELECOM DW ¦ Release Calendar — Year View | [23 empty] | 2026-01-01 | 5 | 31
[24 empty] | 2026-02-01 | 1 | 28
Jira-style year-at-a-glance · release names shown on their Start / Target Deploy dates, colored by Status · pulled live from the Release Calendar sheet | [23 empty] | 2026-03-01 | 1 | 31
| 2026 | ◀ Year — type another year to switch the view | [21 empty] | 2026-04-01 | 4 | 30
[24 empty] | 2026-05-01 | 6 | 31
| January | [7 empty] | February | [7 empty] | March | [6 empty] | 2026-06-01 | 2 | 30
| SUN | MON | TUE | WED | THU | FRI | SAT |  | SUN | MON | TUE | WED | THU | FRI | SAT |  | SUN | MON | TUE | WED | THU | FRI | SAT | 2026-07-01 | 4 | 31
[5 empty] | 2026-01-01 | 2026-01-02 | 2026-01-03 |  | 2026-02-01 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 |  | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-08-01 | 7 | 31
[24 empty] | 2026-09-01 | 3 | 30
| 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 |  | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 |  | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-10-01 | 5 | 31
[24 empty] | 2026-11-01 | 1 | 30
| 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 |  | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 |  | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-12-01 | 3 | 31
| 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 |  | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 |  | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28
| 2026-01-25 | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 | [9 empty] | 2026-03-29 | 2026-03-30 | 2026-03-31
| 2026-01-25: April |  | May | [7 empty] | June
| SUN | MON | TUE | WED | THU | FRI | SAT |  | SUN | MON | TUE | WED | THU | FRI | SAT |  | SUN | MON | TUE | WED | THU | FRI | SAT
|  |  |  | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | [6 empty] | 2026-05-01 | 2026-05-02 |  |  | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06
| 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 |  | 2026-05-03 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 |  | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13
| 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 |  | 2026-05-10 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 |  | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20
| 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 |  | 2026-05-17 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 |  | 2026-06-21 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27
| 2026-04-26 | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 |  |  |  | 2026-05-24 | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 |  | 2026-06-28 | 2026-06-29 | 2026-06-30
2026-05-31
| July | [7 empty] | 2026-05-24: August |  | September
| SUN | MON | TUE | WED | THU | FRI | SAT |  | SUN | MON | TUE | WED | THU | FRI | SAT |  | SUN | MON | TUE | WED | THU | FRI | SAT
|  |  |  | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 |  | 2026-05-30: 2026-08-01 |  |  |  | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05
[19 empty] | ● Reward Hub Ceo Category · Start | ● Daily Kpi Report - Addition of KPIs · Start ● Daily Kpi Report - Addition of KPIs · Target |  | ● Reward Hub Ceo Category · Target
| 2026-07-05 | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 |  | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 |  | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12
[10 empty] | ● Multiplay 90 Days (Pre and Post) · Start | ● BVS Sales Old Age flag Core · Start | [6 empty] | ● Reward Hub - CEO addition · Start | ● Simosa Parent Child Sourcing · Start | ● Daily KPI Report- Addition of App Kpis · Start ● Daily KPI Report- Addition of App Kpis · Target | ● CPS License Log & Daily OFT Report · Start ● Reward Hub - CEO addition · Target
| 2026-07-12 | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 |  | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 |  | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19
[9 empty] | ● live app hierarchy fix · Start ● live app hierarchy fix · Target | ● OMNI API table export · Start |  | ● BVS Sales Old Age flag Semantic · Start ● BVS Sales Old Age flag Core · Target | [7 empty] | ● DFS Lifecycle new columns addition · Start ● DFS Lifecycle new columns addition · Target
| 2026-07-19 | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 |  | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 |  | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26
[10 empty] | ● Addition in Universal Charging Base · Start ● postpaid lifecycle hotfix · Target | ● UCIP_LKP update · Start ● Multiplay 90 Days (Pre and Post) · Target | ● Addition in Universal Charging Base · Target | [5 empty] | ● Rox Achievement Fix · Start ● Rox Achievement Fix · Target | ● CPS License Log & Daily OFT Report · Target | ● NBO Lookup - New Sourcing · Start ● NBO Lookup - New Sourcing · Target |  | ● Sales Fact 5G Date Addition · Start
| 2026-07-26 | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 |  |  | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 |  | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30
[18 empty] | ● Postpaid Conversion API · Start | ● FikrFree New Sourcing · Start | ● postpaid live · Start ● Sales Fact 5G Date Addition · Target
[9 empty] | 2026-08-30 | 2026-08-31
● Jazz Advance TPT Update · Start ● Jazz Advance TPT Update · Target
| October | [7 empty] | 2026-08-23: November |  | December
| SUN | MON | TUE | WED | THU | FRI | SAT |  | SUN | MON | TUE | WED | THU | FRI | SAT |  | SUN | MON | TUE | WED | THU | FRI | SAT
[5 empty] | 2026-10-01 | 2026-10-02 | 2026-10-03 |  | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 |  |  |  | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05
| 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 |  | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 |  | 2026-12-06 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12
● Tamasha IP list update · Start ● Tamasha IP list update · Target
| 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 |  | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 |  | 2026-12-13 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19
|  | ● DFS Lifecycle new columns addition · Start ● DFS Lifecycle new columns addition · Target | ● b2c sales hotfix · Start ● b2c sales hotfix · Target
| 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 |  | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 |  | 2026-12-20 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26
| 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 |  | 2026-11-29 | 2026-11-30 | [6 empty] | 2026-12-27 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31
STATUS LEGEND
On Track | 2026-10-28: At Risk | Delayed |  |  |  | Completed |  |  |  | On Hold
★ Highlighted date = today ¦ Change Year above to view any year ¦ Release names appear directly on their Start / Target Deploy dates, colored by Status.